## Results
Metaswitch SIP Provisioning Server Endpoint Pack Test Plan
Any feature not implemented in the Endpoint Pack and/or not supported by the endpoint should be marked as "Not Valid".
Endpoint Pack | Yealink_T2X_certified |  |  | Progress
Author | Yealink Network Technology Co., Ltd |  |  | Passed | 67
Date Created | 2013-12-15 |  |  | Failed | 0
Date Tested | 2013-12-19 |  |  | Untested | 1
SIP PS Version |  |  |  | Not valid | 3
Tester | zxc |  |  | Complete | 98.59%
Test Feature | Test Case | Method | Completed | Tester's Comments
Loading to EAS | Upload to EAS | Upload the endpoint pack to the EAS and load using the craft interface. Pack must load successfully without error. | Passed
Firmware | Upgrade | Change the firmware version sent to the endpoint to a more recent version, make sure the endpoint upgrades successfully | Passed
| Downgrade | Change the firmware version to a lower release and make sure the endpiont downgrades successfully | Passed
Provisioning | HTTP | Provision an endpoint using SIP PS and HTTP delivery of config | Passed
| HTTPS | Provision an endpoint using SIP PS and HTTPS delivery of config | Passed
| Manual mode | Create a managed device for a subscriber manually, and then provision an endpoint for them. | Untested
| HTTP Digest | Use the HTTP Digest method to authenticate the endpoint, confirm that correct configuration is pulled down. | Passed
| XML App login | Use the XML App to authenticate and login | Not valid
| Polling | Configure the endpiont to poll for new configuration at a specific time. Make changes to the configuration and wait for the endpoint to poll. Confirm that polling occurs at correct time and new config is downloaded | Passed
Basic Call Functionality | Registration | Check SIP flows to ensure the endpoint registers successfully. | Passed
| Simple call | Make an inbound call to the device - check it stays up for >60 seconds. Make an outbound call - check it stays up for >60 seconds. | Passed
| RTP | Confirm that for the simple call test case there is 2-way audio and RTP is negotiated for G.711 | Passed
| Ringtone | Change the ringtone for the device and make sure it uses the new value. | Passed
| Call Waiting | Can the Endpoint Pack toggle the use of call-waiting? | Passed
| Line Description | Configure a name/description for the line and ensure the endpoint displays the appropriate value | Passed
| Packetisation mode | Confirm that the endpoint is configured to use 20ms packetisation mode. | Passed
Soft-keys | Hot-spots | For every hotspot defined in the schema check to make sure that it appears in the right place for the endpoing(s) it's defined for. Clicking on the hotspot(s) should bring up the correct soft-key settings in the UI. | Passed
| Line key | Provision an endpoint with a line-key on a soft-key. Make sure the key works. | Passed
| Speed Dial | Provision an endpoint with a speed-dial soft-key. Make sure the key works. | Passed
| Enhanced Speed Dial | Provision an endpoint with Enhanced Speed Dial on a soft-key. Make sure the key works. | Passed
| Do not disturb | Provision an endpoint with do not disturb soft-key, make sure the key works. | Passed
| Enhanced Monitored Extension | Provision an endpoint with an Enhanced Monitored Extension soft-key and make sure the key works. | Passed
| Enhanced Call Park | Provision an endpoint with Enhanced Call Park on a soft-key. Make sure the key works. | Passed
| Automatic Callback | Provision an endpoint with Automatic callback on a soft-key. Make sure the key works. | Passed
| Automatic Recall | Provision an endpiont with the automatic recall soft-key and ensure it works. | Passed
| Park Call | Provision an endpoint with a call-park soft-key. Make sure the key works. | Passed
| Retrieve Parked Call | Provision an endpoint with a soft-key for retrieving a parked call. Make sure the key works. | Passed
| Trace Call | Provision an endpoint with Trace call on a soft-key. Make sure the key works. | Passed
| Directed Pickup | Provision an endpiont with Directed Pickup on a soft-key. Test that the key works. | Passed
| Group call pickup | Provision an endpoint with Group Call Pickup on a soft-key. Make sure the key works. | Passed
| Last caller ID erasure | Provision an endpoint with Last caller ID erasure functionality on a soft-key. Make sure the key works. | Passed
| Line identification | Provision an endpoint with Line Identification functionality a soft-key. Make sure the key works. | Passed
| Voicemail | Provision an endpoint with a Voicemail soft-key. Make sure the key works. | Passed
| Call list | Provision an endpoint with Call List configured for a soft-key. Make sure the key works. | Passed
| Directory | Provision an endpoint with Directory listing on a soft-key. Check that the key works. | Passed
| Intercom | Provision an endpoint with Intercom on a soft-key. Make sure the key works. | Passed
| Private call hold | Provision an endpoint with Private call hold on a soft-key. Make sure the key works. | Passed
| XML Apps | Provision an endpoint with each of the XML apps that should be supported, confirm they work. | Passed
Endpoint Models | Test all models | The Endpoint Pack should generate valid UI and configuration for all available settings on all supported endpoint models. Because different models might be treated differently the tester may need to run explicit tests against each model. Method: Contact the pack author for differences between models. Additionally, the tester can scan the config template and/or schema metadata in the pack for references to "requestInfo.model" and "supported_models" (respectively). | Passed
XML Apps | Login/logout | Configure the endpoint to use the XML login app for authentication. | Not valid
Authentication | HTTP Digest or XML app | Confirm that all endpionts supported by the pack can be authenticated/provisioned either with HTTP Digest or XML apps (or both). | Passed
| Non-Numeric characters | When authenticating via HTTP Digest the user can enter either their PIN or EAS password. If the endpoint doesn't allow non-numeric values to be entered then the PIN will need to be used, and this should be documented. | Passed
Date/Time | NTP | Configure an NTP server for the endpoint. Confirm that the endpoint displays the correct time-zone | Passed
| Timezone | Change the timzone for the endpoint and make sure the changes are adhered to | Passed
| Format | Make sure that changing the date/time format alters the format used by the endpoint. | Passed
| Daylight Savings | Change the time setting on the endpoint past the next daylight-savings change. Confirm the endpiont correctly deals with the change in daylight-savings | Passed
Group Paging | Sending paging | Configure the endpoints with group paging subscription and appropriate soft-key. Test that they can broadcast a group page. | Passed
| Receiving paging | Configure the endpoints with group paging subscription and appropriate soft-key. Confirm that they can receive a group page. | Passed
Diagnostics | Syslog | Configure an endpoint to send syslog logging. | Passed
| Syslog levels | Repeat previous test with all variations of log-level that are available in the UI. Make sure all work as expected. | Passed
Administration | Web UI | Enable the web UI. Make sure it's accessible. | Passed
| Admin password | Test that the admin password can be configured | Passed
| User password | Check that the user-password can be configured | Passed
Transport | UDP | Configure the device to use UDP for SIP - make sure it works | Passed
| TCP | Configure the device to use TCP for SIP - make sure it works | Passed
Digit Map | Standard test | Configure a digit map for the endpoint so that it can dial 7D, 10D, 1+10D, *xx, *xxx, xxx and xxxx numbers | Passed
MWI | MWI Toggle | Enable and disable MWI subscription for the endpoints. Confirm that the SUBSCRIBE message is/isn't sent in each case. | Passed
Default Values | Sensible | Create a new endpoint in the profile editor screen and make no changes. Provision an endpoint and check the default values that are used, for example: - Web UI is turned off - Admin password is set and is non-simple - Soft-keys are all blank | Passed
Directory | Download | Enable directory download to the endpoint, provision the endpoint and then make sure that it receives the correct directory listing. The values should reflect the names/numbers/extensions of the members of the subscriber's business group. | Not valid
Pack name | Follows Convention | The Endpoint Pack name should follow the Metaswitch guidelines: <vendor>_<family>_<type>_<author> | Passed
MWI | Subscribe | Can the endpint toggle subscription for MWI? | Passed
| Indicator | Can the endpiont toggle MWI indicator light? | Passed
Second Line | Standard test | The test is passed if a second line can be configured on the endpoint. | Passed
Shared Line | Standard test | Does the device support shared line? | Passed
Documentation | Standard test | Does the Endpoint Pack come with appropriate documentation? | Passed
Timers | Registration | Set the registration expiry timer and ensure it's used by the endpoint | Passed
| Registration Renewal | Change the renewal timer and ensure the endpoints use it. | Passed
| Registration failure retry | Make sure the endpoint retries registration failure at the right time | Passed
Network | Media QoS | Set the media QOS value and make sure the endpoint uses it. | Passed
| Signalling QoS | Make sure the pack can configure the signalling QoS value correctly. | Passed
| VLAN tagging | Can the Endpoint Pack set the vlan tagging value? | Passed

## Notes
This spreadsheet details the tests that the ITG goes through when verifying a phone pack for the enhanced SIP Provisioning Server.
Some tests in this list are also covered by a standard certification/accreditation test plan. It is therefore recommended that phone packs are built before standard testing of the end-device. This ensures efficient use of time by avoiding duplication of effort.
The tests that are covered in the certification/accreditation test plans are marked as such.
IMPORTANT NOTE: Phone packs will generally support more than one model of phone. Different models will often be treated slightly differently by the pack. It is therefore important for the tester to consider how every test feature below may affect each phone model in the pack and modify their testing accordingly. Some tests below explicitly mention testing different models where this is most likely to be an issue (e.g. soft-keys).
It is recommended that the tester talk to the pack author about possible model differences, and/or read through the schema/config template to identify areas to pay particular attention to during testing.